## Slide 1: IDEAL-Game Final Meeting 28th- 30th of November 2022, Germany; Paderborn
Last steps to do until the end of the project
University of Paderborn, Chair Business and Human Resources Education II Prof. Dr. Marc Beutner

## Slide 2
IDEAL-GAME
Last steps to do until the end of the project
IDEAL-GAME –
Final Meeting
Host: University of Paderborn, Germany
28th – 30th of November 2022
Project Number: 2020-1-DE01-KA203-005682
Notes: Okay, lets move on to the next agenda item: What’s laying ahead of us?
In a short summary, I will once again present the main construction sites. I may have to adapt the slides, as a lot of new things have now been adapted here.

## Slide 3: Overview – Intellectual Outputs
Notes: So we have this 5 IOs. And currently all IOs are running or even finished yet.

## Slide 4: Project timeline - IOs
December 2020
April
2021
August
2021
December
2021
April 2022
Start of the project
September
2020
- Finish - End of the project December 2022
Intellectual Outputs of the IDEAL GAME project
IO1
01-09-2020 to 28-02-2021
IO2
01-10-2020 to 31-07-2022
IO3
01-06-2021 to 20-05-2022
IO4 01-01-2022 to 01-08-2022
IO5 01-03-2022 to
31-08-2022
August
2022
Ongoing
Ongoing
Ongoing
Complete
Complete
Notes: IO1 has been completed for some time, IO2 is currently being worked on, accompanied by the survey, IO3 seems to be completed in time, but a few games and learning scenarios are still missing. IO4 and IO5 need to be completed in the coming weeks.

## Slide 5: Last steps – Summary IO2
Please have a closer look into the workplan to get further details for next project activities and its deadlines!
Activity 6: Translation |  |  |  |  |  |  |  |  | 
6.1) Translation of text elements that are displayed within the tool | UPB, UPIT, WSEI, UD, UDIMA | Until 30/08/2022 |  |  | Not necessary |  |  |  | 
6.2) Integration of translated text elements | IK, UPB | 30/08/2022 |  |  |  | Not necessary | Not necessary | Not necessary | Not necessary
Activity 7: Showcasing the tool |  |  |  |  |  |  |  |  | 
7.1) Dissemination of tool | All partners | Until 31/10/2022 |  |  |  |  |  |  | 
Notes: This slide gives us an overview of what we still have to work on. Fore more details, please see the work plan.

## Slide 6: Last steps – Summary IO3
Please have a closer look into the workplan to get further details for next project activities and its deadlines!
Activity 6: Translation | 
Translation of Games and Learning Scenarios | The self-created games should be available in the national language as well as in English
Notes: This slide gives us an overview of what we still have to work on. Fore more details, please see the work plan.

## Slide 7
Activity 1: Didactical handbook for lecturers | 
Writing the parts of handbook | All partners
Translation of book into national language | All partners
Creation of book layout and design | IK
Last steps – Summary IO4
Please have a closer look into the workplan to get further details for next project activities and its deadlines!

## Slide 8
Activity 2: Tool handbook for lecturers | 
Writing the parts of handbook | All partners
Translation of book into national language | All partners
Creation of book layout and design | IK
Last steps – Summary IO4
Please have a closer look into the workplan to get further details for next project activities and its deadlines!

## Slide 9
Activity 2: Tool handbook for students | 
Writing the parts of handbook | All partners
Translation of book into national language | All partners
Creation of book layout and design | IK
Last steps – Summary IO4
Please have a closer look into the workplan to get further details for next project activities and its deadlines!

## Slide 10
Last steps – Summary IO5
Please have a closer look into the workplan to get further details for next project activities and its deadlines!
Activity 1: Policy Paper |  |  |  |  |  |  |  | 
Writing parts and providing to UPIT | All partners | 30.06.2022 | ✓ | ✓ | Not necessary |  |  | 
Writing Policy Paper | UPIT | 30.07.2022 |  |  |  |  |  | 
Translation of Policy Paper | UPB, UPIT, WSEI, UD, UDIMA | 30.08.2022 |  |  |  |  |  | 
Creation of layout and graphics | IK | 30.09.2022 |  |  |  |  |  | 
Activity 2: Layman´s report |  |  |  |  |  |  |  | 
Writing Layman´s Report | UPIT | 30.07.2022 |  |  |  |  |  | 
Translation of Policy Paper | UPB, UPIT, WSEI, UD, UDIMA | 30.08.2022 |  |  |  |  |  | 
Creation of layout and graphics | IK | 30.09.2022 |  |  |  |  |  | 

## Slide 11: Last steps - Summary
Please have a closer look into the workplan to get further details for next project activities and its deadlines!
IO2: Development of the Creator Tool
Translation & Showcasing the Tool
IO3: Creation of OER Serious Games as well as learning materials and implementation strategies
Translation of Games and Learning Scenarios
IO4: Development of Books (Didactical handbook, tool handbook for lecturers and students)
Writing parts and Translation of the books
IO5: Policy Paper and Layman‘s Report
Translation of the Reports
Notes: This slide gives us an overview of what we still have to work on. Fore more details, please see the work plan.

## Slide 12: Dissemination
Please disseminate the project and their results broadly.
Feel free to contact us for more dissemination ideas
Website: https://ideal-game.eduproject.eu/
Facebook: Erasmus+ - Project IDEAL GAME
Notes: Please also continue your dissemination activities. If you have not yet done so. Connect with us on Facebook.

## Slide 13
Contact
Marc Beutner University Paderborn, Warburger Str. 100 33098 Paderborn, Germany Marc.Beutner@uni-paderborn.de
https://wiwi.uni-paderborn.de/department5/wirtschaftspaedagogik-prof-beutner

## Slide 14
Thank you very much for
your attention!